Planning Cycle Timeline

2024 IASI Championship Meets

| Fall Coaches Meeting | Coaches Committee will establish preferences for the Course, Dates, and Locations for Championship series meets |
| --- | --- |
| September 6, 2022 | Technical Planning Committee Meeting |
| Between Coaches Meeting & Early-December | Office coordinates with preferred facilities and seeks to establish contracts |
| November 8, 2022 | Technical Planning Committee Meeting |
| By December 31, 2022 | Coaches solidify the Course, Dates, and Locations of the Championship series meets |
| January 10, 2023 | Technical Planning Committee Meeting |
| March 14, 2023 | Technical Planning Committee Meeting |
| Mid-March 2023 | 2023-24 Meet Bid Meeting. Establish the meet schedule for the 2023-24 Winter Season and the 2024 Summer Season, including the hosts for the IASI Championship meets. |
| By April 30, 2023 | Receive parameters, desires, and expectations from the Age Group Committee, Athletes Committee, Coaches Committee, Officials Committee, and Senior Committee |
| May 9, 2023 | Technical Planning Committee Meeting |
| June 11, 2023 | Technical Planning Committee Meeting |
| By August 31, 2023 | Complete the planning process for all aspects of the 2024 Championship series meets, and submit to the Board of Directors for evaluation |
| By September 20, 2023 | Board of Directors approval by date, establishing the format for the 2024 Championship series meets |
| Between October 1 - October 23, 2023 | Technical Planning Committee collaborates with the Sanctioning Committee liaison to revise and review the Template Meet Announcement documents |
| By October 24, 2023 | Provide the Sanctioning Committee with Template Meet Announcements |
| By October 31, 2023 | Sanctioning Committee distributes the editable Template Meet Announcement documents to the host clubs of the 2024 Championship series meets |