South Carolina Swim Club
Strategic Plan Resolution (2025–2026)

## #1 Promoting Outstanding Volunteer Support

Goal: Build a culture of true buy-in and engagement — moving beyond the minimum requirement toward real ownership in the club’s mission.

Key Targets:
• 50% of families meeting volunteer service points by year-end (up from ~20%).
• Year of socials scheduled, with attendance growing at least 20% annually.
• Alumni network launched with at least 20 engaged members by end of Year 1.

Tracking & Accountability:
• Standalone Year-Long Volunteer Database (outside TeamUnify).
• Kelsey: Volunteer systems & family education.
• Laurie: Culture-building (videos, pep rallies, tailgates, service projects).

## #2 Establishing State-of-the-Art Facilities

Goal: Secure more water in the short term and lay the foundation for a long-term SCSC home facility.

Short-Term (James):
• Expand lane capacity within 1 year to enable team growth.

Long-Term (Matthew):
• Develop vision & feasibility for a 50m facility with warm-up/warm-down pools and bleachers.
• Engage CCSD, Town of Mt. Pleasant, CofC, CVB, and municipalities in discussions.

Milestones:
• 3 months → Action Forces formed.
• 6 months → Feasibility study & awareness campaign.
• 12 months → Capital campaign kickoff.

Reporting:
• Both Action Forces (short- and long-term) report monthly to the Board.

## #3 Inspiring Every Individual to Achieve the Highest Potential of Personal Development

Goal: Ensure every swimmer has the chance to succeed and thrive — both in the pool and personally.

Key Priorities:
• Retention and motivation (track year-over-year retention & attrition).
• Building a ‘culture of support’ among teammates.
• Helping athletes track goals beyond times (effort, technique, character, leadership).
• Parent education on supporting athletes in healthy, positive ways.

Action Items & Accountability:
• Sara: Accountable for individual written development plans; Booster Club executes tracking/recognition.
• Stephanie: Dual-track mentorship program — swimmer-to-swimmer and family-to-family, with pairings structured to multiply connections.
• Brad: Clinics — written plan within 3 months; discretion to expand focus from technical skill to mental training, nutrition, and leadership.

Recognition Programs:
• Awards, shout-outs, mentorship pairings, and team-wide acknowledgment of progress.