## Sheet1
SOUTHEASTERN SWIMMING BOARD OF DIRECTORS 2016 – 2021 STRATEGIC WORKSHEET: OCTOBER 2016
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Increase number of parent volunteers | Average number of volunteers working a meet = 10% of full time swimmers in the meet | Post Meet Report - Determine number of swimmers per host team. Collect number of volunteers from host club for that meet | Publicize program Educate clubs Coordinate tracking system | Volunteer Coordinator TBD | Begin program Jan 2017 | 100
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Recognize those officials who have substantialy worked more than the minimum number of sessions per year | Increase the number of officials who work well above the minimum sessions required. | OTS - Determine number of sessions worked per official on each club. | Procure gifts for officials working 100+ and 75+ sessions per calendar year | Officials Committee Athlete Committee | Have program in place for awards in February 2017 for the 2016 calendar year. | $500 Total
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Reward the club with the most newly certified officials during the previous year | OTS Reports – Determine number of newly certified officials for previous year. Officials = over 8% of full time swimmers on team | Status reports to clubs in January showing how many new officials became certified for their club during the previous year. Recruitment brochures made available to each club at October 2016 LSC meeting. | In January, the Officials Committee will determine which of the SES clubs had the most newly certified officials during the previous year, separated in one of three club sizes - Small/Medium/Large. The Athletes Committee will fund. | Officials Committee Athlete Committee | Have program in place for awards in February 2018 for the 2017 calendar year. | 100
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Increase Cash Reserves to exceed our highest six month operating expenses looking back over 4 years | Average cash reserves exceed 6-month operating expenses | Adjust surcharge to increase cash available to SES | Determine highest 6-month operating expense over the last quad. Determine our cash reserve | Treasurer | Have program in place for beginning 2017.
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Increase the number of delegates to the USAS Sports Convention | Encourage & fund at least 3 additional delegates to Convention | SES BOD agree to fund additional delegates to convention | Make Request Form to attend Convention available on website. | BOD SES General Chair SES Executive Secretary | Request Form on website by 31 July 2016. BOD Approves Funds NLT 31 July 2016 . General Chair selects additional delegates to Convention | We're already doing this but not on paper.
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Encourage SES clubs to host Diversity meets | Two Diversity meets within the LSC annually | General encouragement to SES clubs on the advantage of hosting Diversity meets, working with the community and getting recognition through the local media | Two or more Diversity meets to be run within the LSC boundary annually | SES President Adapted Swimming Coordinator Diversity Coordinator | Have program in place for 2017 -18 season. PNY sping meet is on the schedule
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Formalize Athlete Committee | Athlete Committee meets at least twice per year coinciding with SC and LC Championship meets Create Athlete Newsletter highlighting individual athletes within the LSC and providing subject matter of importance to our athletes | BOD provides funds to Athlete Committee, with oversight Athlete Committee determines athlete members to SES Committees Athlete Committee determines the method of distributing Athlete newsletter or posting on the SES website | 1- Formal Athlete Committee formed 2-Athlete Committee makes plans to start holding Committee meetings 3-Athlete Committee makes plans for first Athlete newsletter | Athlete Representatives | Initial plans made during LC Championship meet in 2017, for full program to start in 2018.
Jan to do a session in the Spring of 2018 in Huntsvile. To be determined at the Fall meeting
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Award Top Performing Clubs that participate in the Virtual Club Championship | 20% of clubs participating in program, increasing an additional 5% per year for the quad | Publish document supporting VCC . Encourage head coaches to paticipate . Put info on website showing which clubs participated and who the winners were | Create document Determine cash prize Specific item at BOD/HOD Mtg | Senior Vice Chair Age Group Vice Chair Coaches Representative | Already on the webpage, announce publish fall meeting.
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Establish a strong athlete mentorship program within the LSC | Have 5 % of our athletes participate the first year, then an additional 2% each year through the quad | Athlete Committee devise a plan, then put ion SES website. | Devise a mentorship program Add program to Athlete newaletter Have gist of program put on SES website | Athlete Committee | Have program ready to go Jan 2018
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Put 2 SES athletes into 2020 Olympics | Put 120 SES athletes into 2020 Olympic Trials, 60 of each gender | Develop our athletes so that they are in the top 20 of each event in the 2020 US Olympic Trials | Encourage participation in Futures, Arena Pro, Junior Nationals, US Open and Senior National meets for all our athletes. | Coaches Committee All SE Head Coaches | Starting after the SE LC Championships and continuous thru summer of 2020.
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Increase Safe Sport Awareness in SES | Schedule at least four Safe Sport presentations in the next four years | Set up a speaker for at least two presentations over the next four years | 1-Set up one presentation to coincide with our bi-annual swimposium 2-Set up one presentation to coincide with a HOD meeting | Safe Sport Coordinator | Start planning nown for program to start in late 2016 or early 2017 for next Hall of Fame weekend
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Create a swim guide which includes directions and/or important information about the meet facilities in SES | Create s swim guide, then publish on website prior to the SE LC Championship in 2017 | 1-Research the pools used by all clubs in the SE area, write a short description of the facilities, then directions to each facility 2-Post on the SE website | Contact each club in the SE geographic area and start listing each club's details | Athlete Committee | Start acquiring data in 2017 for publish and update as needed.
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
At least 75% of SE registered athletes participate in a competitive swim meet | Determine the total number of registered swimmers in each club, then determine how many of those swimmers participate in sanctioned swim meets | Use SWIMS to determine numbers of swimmers in each club and to determine how many of their swimmers actually participate in sanctioned swim meets | Use SWIMS to determine numbers of swimmers in each club and to determine how many of their swimmers actually participate in sanctioned swim meets | Age Group Vice Chair | Start acquiring data now and finalize by June 2017, use leap program for numbers - use for Club Incentive program
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
Have 20% of the SE registered swimmers obtain an IMX score | Determine how many of our swimmers have an IMX score now and what we can do in the LSC to increase the number to a 20% level | 1-Determine where we as an LSC are now and 2-Explore options to advance SE to the pint where 20% of our athletes have an IMX score | Determine whether conducting IMX swim meets or integrating IMX events into swim meets will gain our objective | Age Group Vice Chair | Start acquiring data now and finalize by June 2017. Use LEAP program-use for for incentive program
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones
STRATEGIC GOAL | MEASURABLE OBJECTIVES | ACTION STEPS | TASK What needs to be done? | Responsible Party | WHEN? Deadlines/Milestones